## Roadmap Overview
Month | Phase | Main Goals | Backend Focus (Go) | Frontend Focus (HTML/CSS/JS) | Infrastructure / DevOps | Milestone Outcome
Month 1 | Foundation | Finalize architecture & core setup | Project structure, config, logging, middleware, health endpoint | Base layout, reusable UI components, basic design system | Nginx config, domain setup, server environment prep | Backend skeleton running in production
Month 2 | Core Modules I | Implement DNS & IP tools | DNS lookup module, IP lookup module, validation & error handling | Forms, API integration, result rendering UI | Basic monitoring & log inspection | DNS & IP tools live
Month 3 | Core Modules II | Implement SSL suite | SSL checker, certificate parser, CSR tools | Advanced result formatting, copy/export features | Security hardening, rate limiting | SSL tools fully functional
Month 4 | Advanced Tools | Redirect & mixed content tools | Redirect analyzer, HTTP header parsing | UX improvements, loading states, error UI polish | Server optimization, timeout tuning | Full toolset available
Month 5 | Optimization & Stability | Performance & security improvements | Caching layer, timeout management, input validation strengthening | Performance optimization, mobile responsiveness polish | Load testing, Nginx tuning | Stable production-ready platform
Month 6 | Production Polish & Launch | Testing, documentation, release prep | Code refactor, logging improvements, graceful shutdown validation | Final UI refinement, SEO improvements | Deployment automation, backup strategy | Official production launch